HAIR RAP BY YOYO

PHASE 1 PRODUCT SCOPE,
DELIVERY BASELINE & EXECUTIVE SIGN-OFF

One authoritative management view of what Phase 1 includes, how it will be delivered, what is excluded, and how changes are controlled.

PURPOSE OF THIS DOCUMENT To remove ambiguity before development begins. This document summarizes the approved Phase 1 baseline across the Admin Panel, Artist App and Client Booking App and records the operating assumptions, source hierarchy, delivery model, change-control expectations and executive approvals needed to protect the 50-day deployment plan.

| Document Control | Value |
| --- | --- |
| Document Owner | Business Analysis / Product Delivery |
| Version | 1.0 |
| Date | 19 August 2026 |
| Scope | YOYO Phase 1 - all three products |
| Status | For CEO Review and Formal Confirmation |
| Delivery Target | 50-day deployment-ready plan, commencing from formal approval and scope freeze |

Prepared for Executive Confirmation

# 1. Executive Summary - What Phase 1 Actually Is

Phase 1 is one integrated salon operating platform delivered through three user-facing products that share the same backend, database, business rules and live operational data. It is not three separate systems.

| Product | Primary Users | Phase 1 Purpose |
| --- | --- | --- |
| Admin Panel | Receptionist, Admin, Super Admin | Salon operations, bookings/calendar, clients, artists, services, inventory, POS/billing, memberships, reports, expenses, support, settings and operational controls. |
| Artist App | Artists | Assigned appointments, consultation/review, consent readiness, service-session execution, timers, product add-to-bill, client context and artist-facing catalogue functions. |
| Client Booking App | Clients / Members | Service discovery, solo/group booking, artist preference, live availability, advance payment, memberships, products, bookings, profile and client support journeys. |

THE SIMPLE ARCHITECTURE One PostgreSQL data model + one shared backend/API layer + three interfaces. A booking created in the Client Booking App appears in the Admin Panel and Artist App from the same source of truth; there are no independent copies of booking, client, payment or membership data.

## Executive decision requested

Confirm the Phase 1 scope described in this document as the delivery baseline.

Confirm that approved FSD Main Success Scenarios remain the intended user-flow baseline, while newer approved contracts/state machines supersede any older conflicting rule.

Confirm that UI/UX may be refined during implementation without reopening backend architecture unless the proposed UI change alters business behaviour, data, permissions or APIs.

Confirm the 50-day delivery plan begins from formal approval/scope freeze and that subsequent scope changes or delayed decisions may shift the planned deployment date.

# 2. Source of Truth and Document Hierarchy

The project has accumulated discovery documents, FSDs, ERDs and newer development contracts. To prevent different developers or AI agents from implementing different versions of the product, the following hierarchy applies.

| Priority | Document / Source | How it is used |
| --- | --- | --- |
| 1 | Approved August 2026 business decisions and this signed baseline | Highest business authority for Phase 1 scope and decisions. |
| 2 | Latest development contracts: ERD v2.2, API Contract, RBAC, Booking/Availability v1.1, state machines, Money Rules, Consultation/Consent, Validation/Error Contract | Authoritative technical and runtime behaviour where newer than the FSD. |
| 3 | Phase 1 FSDs - Admin Panel, Artist App, Client Booking App | Authoritative screen/use-case baseline, including Main Success Scenario, actor, trigger, preconditions, postconditions, extensions, functional requirements and fields. |
| 4 | Phase 1 BRD | Business context and overarching requirements; FSD/contracts govern implementation detail. |
| 5 | Stakeholder discovery documents / older ERDs / older Phase 2 combined FRD | Reference only; not authority where superseded by later approved documentation. |

DEVELOPER / HERMES RULE If two documents conflict, do not guess and do not silently merge them. Apply the hierarchy above. If the conflict remains unresolved, stop that work item and raise a decision request to the BA/Product Owner.

## Why the Main Success Scenario still matters

The FSD Main Success Scenario defines the intended user journey and is the first reference for screen-to-screen flow. The newer contracts do not replace good UX flows; they make the underlying business behaviour more precise. Example: an FSD can define the steps of starting a service, while the Session State Machine defines the exact readiness gates that must be true before the Start Session action succeeds.

# 3. UI/UX Position - Freeze the Flow, Not Every Pixel

The UI/UX team has designed the products around the FSD flows. For delivery planning, the FSD Main Success Scenarios are treated as the baseline journeys. UI changes during implementation are expected and should be quick as long as they do not change the underlying business contract.

| Type of change | Example | Impact |
| --- | --- | --- |
| Visual / presentation only | Spacing, colours, card layout, typography, icon, modal size, responsive arrangement | Frontend/App only. No backend contract change. |
| Interaction refinement | Move a button, convert a page to a modal, improve filter placement, simplify a form without changing required data | Normally frontend/app only. |
| Behavioural change | Allow a new actor to perform an action, change when payment is required, change booking assignment behaviour | Requires BA review and usually contract/RBAC/state-machine update. |
| Data/API change | Add a new persisted field, new status, new transaction, new resource relationship | Requires API/ERD validation and controlled change. |
| New scope | New module, new role, new accounting system, new Phase 2 feature | Not part of Phase 1 unless formally approved as a scope change. |

PRACTICAL RULE Do not delay backend development waiting for pixel-level UI perfection. Build against the approved flow and contracts. UI can evolve quickly. Only changes that alter behaviour, data, permissions or financial rules should reopen the backend specification.

The current Admin design set is broad and covers major operational areas; however, individual screens that conflict with newer approved rules (for example custom role creation in a Phase 1 fixed-role model) must follow the newer approved contract rather than the older visual concept.

# 4. Product 1 - Admin Panel Phase 1 Overview

The Admin Panel is the operational command centre for salon staff. It supports day-to-day reception operations, management controls, financial transaction visibility and controlled configuration based on role.

| Domain | Phase 1 capability |
| --- | --- |
| Authentication & Access | Login, verification, profile, session/security states, fixed-role access model. |
| Dashboard & Calendar | Operational dashboard, appointments/calendar, upcoming appointments and salon-level visibility. |
| Bookings & Walk-ins | Create/manage bookings, walk-in handling, check-in, client lookup and operational appointment actions. |
| Manual Artist Assignment | Auto Assign / YOYO Assigned Team enters a manual assignment queue. Authorized Admin/Floor Manager selects eligible artist(s); Receptionist cannot assign. |
| Clients | Client list/search, client profile, booking history, wallet/membership context, consultation history and saved-address reference. |
| Artists | Artist roster, profile, service qualifications, schedules/availability inputs and status management. |
| Services & Catalogue | Service categories/subcategories/services, duration, pricing/configuration and artist eligibility. |
| Inventory & Products | Product catalogue, stock movements, low stock, expiry and related catalogue administration. |
| POS, Billing & Invoices | Session billing, products/add-ons, payment collection, final invoice, invoice search/view/reprint. |
| Payments & Refunds | Payment status, reconciliation visibility and controlled refund workflow. |
| Memberships | Sell/assign memberships, member management, balance/ledger visibility and membership operations under approved controls. |
| Expenses & Finance Reports | Daily expense submission/review, expense report, invoice report, revenue report; no full general-ledger accounting in Phase 1. |
| Support & Content | Support tickets, Trendsetter queries, content overrides and notifications. |
| Settings | Operational settings; critical financial/security configuration restricted to Super Admin. |

# 5. Product 2 - Artist App Phase 1 Overview

The Artist App is deliberately scoped to the artist's own work. It is not an unrestricted CRM or admin application.

| Journey / Module | Phase 1 behaviour |
| --- | --- |
| Authentication & Profile | Artist authentication and own-profile context. |
| My Appointments | Today / Upcoming / Completed appointment views sourced from the same live booking data as Admin. |
| Client Arrived / Readiness | Artist sees assigned booking/service context and can proceed only when required business gates are satisfied. |
| Consultation | New client: full consultation by artist. Returning client: prior consultation visible; artist records No Changes review or an updated consultation. History remains immutable. |
| Consent | High-risk service requires client digital service consent before Start Session. Media consent is separate and optional; it never blocks service. |
| Start Session | Allowed only when booking is checked in, service is fully assigned, consultation/review is satisfied and required high-risk consent exists. |
| Active Session | Persisted service session with timer, participants and event history. Parallel services can have separate concurrent sessions where approved. |
| Two-Artist Service | Both required artists must be assigned before start. Lead/support participation is supported in the service-level session model. |
| Product Add-to-Bill | Artist may add appropriate products to the bill during an active service; it is an explicit action, never automatic. |
| Ready for Billing | Session/service completion feeds POS/billing; session records and events remain auditable. |
| Products | Artist-facing product catalogue access according to scope. |
| Client Data Scope | Artist may access only the client/session information needed for assigned/current work - not unrestricted client records. |

# 6. Product 3 - Client Booking App Phase 1 Overview

The Client Booking App provides the consumer journey into the same booking, payment and membership engine used by salon staff.

| Journey / Module | Phase 1 behaviour |
| --- | --- |
| Account & Profile | Authentication, profile, booking history, addresses and client-owned data. |
| Service Discovery | Browse services/categories and relevant client-facing content. |
| Solo Booking | Select service(s), date/time and artist preference; live availability is checked against shared capacity. |
| Artist Preference | Specific artist may be requested/selected. Auto Assign / YOYO Assigned Team does not auto-select a named artist in Phase 1; staff assigns manually after booking. |
| Multi-Service Booking | One booking may contain several services with different artists and approved parallel execution. |
| Two-Artist Service | A service may require two artists. Client-requested artist can be retained as lead while support is assigned operationally. |
| Group Booking | Up to five participants including organizer, with participant-level service/time/advance traceability. |
| Availability Rules | 15-minute slot interval, 10-minute post-service artist buffer, 60-day horizon, 30-minute client same-day lead time and server-side holds during payment. |
| Advance Payment | Standard booking advance is 20% of approved booking service amount; specifically requested Creative Director booking uses fixed INR 5,000 rule. Advance is online via Razorpay. |
| My Bookings | Upcoming / completed / cancelled history with allowed cancellation/reschedule paths subject to current rules. |
| Membership | View/purchase approved membership tiers and use selected membership stored value according to ledger rules. |
| Products | Retail product discovery/purchase path where applicable to Phase 1. |
| Trendsetter / Support | Client enquiry and support entry points that feed Admin-side workflows. |
| My Bio | Read-only view of relevant consultation-derived data; client does not author the salon consultation. |

# 7. Core Cross-Product Business Rules - Locked Phase 1 Baseline

| Rule Area | Approved Phase 1 baseline |
| --- | --- |
| Shared source of truth | All three products read/write the same authoritative backend data; no independent booking/payment/client copies. |
| Service scheduling | One booking can contain multiple services. Different services can use different artists. Approved hair/beauty services may run in parallel. Same artist never overlaps. |
| Slot & buffer | Minimum booking interval 15 minutes. Every service has a 10-minute artist buffer after execution. |
| Booking horizon | Client booking horizon 60 days; same-day self-booking minimum lead 30 minutes. |
| Specific artist | Specific artist can be selected up to 60 days. Bookings 31-60 days out are provisional and revalidated around T-30. |
| Artist unavailable | No silent replacement. Client is informed and chooses same artist/new time or same time/different available artist. |
| Auto Assign | No Phase 1 automatic ranking/selection algorithm. Booking enters manual staff assignment queue. |
| Assignment gate | Check-in does not assign. Start Session is blocked until required service assignment is complete. |
| Two-artist service | Service master can require one or two artists. Both capacity requirements are validated. |
| Advance | 20% for standard pre-booked paths. Specific Creative Director booking uses INR 5,000 fixed advance. Auto Assign remains 20% even if a Creative Director is later manually assigned. |
| Hold | Payment hold is server-side, 8 minutes. Late payment capture cannot overbook; it enters reconciliation handling. |
| Consultation | Completed by artist, not client. Returning-client history is reused through No Changes review or updated via a new immutable consultation record. |
| Consent | High-risk service consent is a pre-session gate. Media consent is separate and optional. |
| Invoices | Before close: operational editing permitted. After close: invoice history is locked; corrections use controlled financial actions, not destructive editing. |
| Membership | Prepaid stored-value model with ledger. Client/reception chooses which membership to use; system does not silently drain another membership/wallet. |
| Tips | Client-originated; no silent equal split across artists. |
| Audit | Sensitive financial, assignment, consultation, consent, session and configuration actions are auditable. |

# 8. Phase 1 Finance - What It Includes and What It Does Not

Phase 1 finance is salon transactional finance and operational reporting. It is intentionally not a full accounting/ERP replacement.

| Included in Phase 1 | Not included in Phase 1 baseline |
| --- | --- |
| Session checkout / POS | General Ledger / Chart of Accounts |
| Client invoices and invoice history | Trial Balance |
| Vendor invoice records | Full Balance Sheet / Cash Flow accounting suite |
| Payment status and reconciliation handling | Bank reconciliation engine |
| Cash / Card / UPI final settlement records | Statutory payroll/accounting engine |
| Razorpay booking advance and verified webhooks | Zoho Books integration unless later approved |
| Refund workflow with Admin approval | Assets / Loans module |
| Membership and wallet stored-value ledgers | Phase 2 approval-routing complexity beyond the approved Phase 1 expense model |
| Daily expenses with maker/checker controls | Full Accountant role |
| Revenue allocation by artist | Automated payroll/commission calculation |
| Expense / Invoice / Revenue reports | Full enterprise accounting close process |

FINANCIAL CONTROL Closed invoices are not directly rewritten. Refunds/corrections remain traceable. Reception can perform normal operational billing; Admin handles approval/correction workflows; Super Admin controls critical financial configuration.

# 9. Access Model and Separation of Duties

| Role / Principal | Phase 1 responsibility |
| --- | --- |
| Receptionist | Daily operations: bookings, client search, check-in, POS/payment collection, membership sale, allowed expense submission and other operational workflows. Cannot approve refunds or perform manual Auto Assign artist allocation. |
| Admin | Receptionist capabilities plus operational management, artist/service/inventory controls, Floor Manager assignment capability, refund approval, expense review/approval, support resolution and broad reporting. |
| Super Admin | Admin capabilities plus user/access administration, critical financial configuration, security settings and other restricted configuration. |
| Floor Manager capability | Operational capability within Admin/Super Admin - not a separate Phase 1 authentication role. |
| Artist | Only assigned/current work and required client/session data; cannot edit invoices, refunds, membership balances, expenses or privileged configuration. |
| Client | Own bookings, profile, payments, membership and client-facing actions only. |

NO CUSTOM ROLES IN PHASE 1 The Phase 1 security baseline uses fixed staff roles. Any visual screen suggesting arbitrary custom role creation is not implementation authority unless the CEO formally approves a scope change.

# 10. Explicit Phase 1 Exclusions / Phase 2 Boundary

The following are not to be silently added to Phase 1 because they materially expand architecture, permissions, testing or delivery risk.

| Deferred / Outside Phase 1 | Notes |
| --- | --- |
| Automatic artist allocation algorithm | Phase 1 is manual assignment. Automated recency/revenue/fairness ranking is Phase 2. |
| Micro Inventory consumption at session level | Phase 2 extension; Phase 1 session architecture remains forward-compatible. |
| Leave management / attendance / day-off swap workflows | Phase 2. |
| Payroll / commission engine | Phase 2. |
| PARISBEANS operational module and Barista role | Phase 2; Phase 1 may retain billing/data compatibility where already required. |
| Booking chatbot | Phase 2 conversational interface over the same booking engine. |
| Full Accountant / Zoho Books / GL suite | Not Phase 1 unless separately approved. |
| Assets / Loans | Phase 2 or future finance expansion. |
| CEO-defined additional membership perks | Not to be invented by developers; current approved membership baseline stands until CEO decision. |
| Multi-branch architecture | Phase 1 is single-branch. |
| Custom role builder | Not Phase 1 fixed-role baseline. |

SCOPE PROTECTION A useful idea is not automatically a Phase 1 requirement. Any new feature added after scope freeze must be assessed for schedule, API, database, testing and deployment impact before commitment.

# 11. 50-Day Delivery Model and Team Responsibility

The approved delivery concept uses a small human engineering team with heavy AI-agent execution. Hermes/DeepSeek is a force multiplier, not the final authority.

| Owner | Primary responsibility |
| --- | --- |
| Backend Developer | Backend architecture, PostgreSQL/migrations, shared APIs, security, RBAC enforcement, transactions, booking/payment invariants, integrations, agent review and production reliability. |
| Frontend Developer | Admin Panel implementation, design system, frontend state, responsive behaviour, API integration, accessibility and review of Hermes-generated frontend work. |
| App Developer | Artist App + Client Booking App implementation, mobile state/navigation, API integration, payment handoff, device behaviour and app-specific QA. |
| Hermes Agents + DeepSeek v4 Flash | Approximately 60-70% of repetitive implementation/test/audit volume: bounded features, CRUD, integration wiring, test generation, contract checking, adversarial regression and documentation. Agents work in isolated branches/worktrees and do not redefine business rules. |
| BA / Product Delivery | Requirements authority, decision register, contract maintenance, scope control, UAT coordination, CEO decisions and acceptance evidence. |
| CEO / Business Owner | Scope approval, unresolved business decisions, timely confirmations and final business acceptance. |

## Milestone intent

| Period | Target |
| --- | --- |
| Days 1-5 | Foundation, scope freeze, architecture, CI, auth/RBAC, final remaining delivery documents. |
| Days 6-15 | Core backend engine + parallel frontend/app shell and primary flows. |
| Days 16-23 | Payments, POS, membership, refunds and finance integration. |
| Days 20-30/32 | Remaining modules and feature-complete candidate. |
| Days 29-35 | Full cross-product integration. |
| Days 36-42 | Autonomous regression swarm + human defect triage. |
| Days 43-46 | Real UAT across Receptionist/Admin/Artist/Client. |
| Days 47-49 | Production rehearsal, rollback, readiness gate. |
| Day 50 | Controlled production deployment and smoke verification. |

# 12. Hermes Graph Loop - How Autonomous Work Is Controlled

Each agent task is bounded by a contract slice. Autonomous work is allowed inside the slice; interpretation of unresolved business scope is not.

| Loop Stage | Required output |
| --- | --- |
| 1. Contract Packet | Relevant FSD Main Success Scenario + API + ERD + RBAC + state machine + validation rules + UI reference. |
| 2. Plan | Agent states files/components/endpoints to change and expected tests. |
| 3. Implement | Agent implements only the approved slice in its branch/worktree. |
| 4. Self-Test | Unit/integration/UI tests and build/lint/type checks. |
| 5. Contract Verify | Agent compares implementation with authoritative requirements. |
| 6. Adversarial Review | A different agent attempts to break the feature: RBAC, concurrency, money, state transitions, validation. |
| 7. Fix & Regression | Evidence-backed defects are fixed and affected tests rerun. |
| 8. Report | Changed files, tests, evidence, unresolved risk and any contract drift. |
| 9. Human Gate | Responsible developer reviews diff/evidence and approves merge. Critical money/security/production decisions remain human-controlled. |

NO "AGENT SAID DONE" ACCEPTANCE Completion is based on evidence: code diff, tests, runtime proof and contract verification. AI-agent completion statements without evidence are not accepted as project completion.

# 13. Delivery Assumptions, Dependencies and Open Business Decisions

The 50-day plan is achievable only if the baseline assumptions remain true. This section makes those assumptions explicit so schedule impact is not hidden.

| Area | Assumption / dependency | Impact if delayed or changed |
| --- | --- | --- |
| Scope | Phase 1 scope is frozen after initial execution gate. | New modules/business rules require re-estimation and may move deployment. |
| CEO approvals | Required business decisions are answered promptly. | Blocked tasks cannot be safely guessed; schedule shifts accordingly. |
| Team availability | 1 Backend + 1 Admin Frontend + 1 App Developer remain substantially available. | Loss of a core owner reduces review/integration throughput. |
| Hermes availability | Agent environment/model budget supports continuous bounded execution. | Humans absorb more implementation volume; schedule risk rises. |
| UI/UX | FSD flows remain valid; pixel-level refinements do not redefine behaviour. | Behavioural UI change requires contract review. |
| Razorpay | Credentials/sandbox/live setup supplied in time. | Payment E2E/go-live can be blocked. |
| Meta / messaging | Required WhatsApp/notification configuration supplied in time. | Notification go-live can be delayed; core booking may still be testable. |
| Business configuration | Services, prices, artist eligibility, schedules, membership values and other required masters are confirmed. | Seed/UAT cannot represent real operations. |
| Tax/GST/HSN | Exact production finance configuration is business/finance-confirmed. | Invoice production launch cannot be signed off safely. |
| Membership expiry treatment | Unused value at one-year expiry remains a business decision unless resolved before affected feature finalization. | Relevant renewal/expiry edge cases remain gated. |
| UAT availability | Real salon users participate in Days 43-46. | Launch confidence falls; deployment may need to move. |

# 14. Change Control - How New Requests Affect the 50-Day Commitment

The project can move quickly because the business and technical contracts are being frozen. The same speed cannot be preserved if material requirements continue to change without schedule impact.

| Change class | Treatment |
| --- | --- |
| Class A - UI-only | Implement within normal frontend/app work. No formal re-baseline unless materially large. |
| Class B - Minor behaviour within existing data/API | BA + developer review. Update affected acceptance criteria/contract if needed. |
| Class C - API/RBAC/state-machine/data change | Formal impact assessment; update authoritative document(s), tests and delivery plan. |
| Class D - New module / Phase 2 promotion / major commercial rule | CEO approval + schedule/cost impact acceptance before implementation. |

SCHEDULE PRINCIPLE The 50-day timeline commences from formal approval of the Phase 1 baseline. Delayed approvals, unresolved business decisions or newly approved scope changes have a corresponding impact on execution sequencing and may proportionately shift the planned deployment date.

## Minimum change request record

Requested change and business reason

Requested by / approval owner

Affected product(s) and FSD use case(s)

Backend/API/ERD/RBAC/state impact

UI impact

Testing/UAT impact

Schedule impact

Approved / deferred / rejected decision and date

# 15. Definition of Deployment-Ready

A feature being coded is not the same as the product being deployment-ready. Phase 1 should be considered deployment-ready only when the following evidence exists.

| Gate | Expected evidence |
| --- | --- |
| Scope & traceability | Approved baseline + RTM links requirements to implementation and tests. |
| Functional coverage | All committed Phase 1 Main Success Scenarios implemented or formally deferred. |
| Booking integrity | Availability, holds, buffer, manual assignment, group/two-artist and state transitions pass. |
| Financial integrity | Advance, POS, invoices, payment capture, refunds, memberships/wallet, expenses and revenue allocation pass invariants and reconciliation tests. |
| Security/RBAC | Frontend visibility plus backend authorization and resource scope tests pass. |
| Cross-product consistency | Admin, Artist and Client apps operate on the same live data and states. |
| Error/recovery | Validation, idempotency, retry, late webhook and concurrency handling pass. |
| UAT | Receptionist, Admin/Floor Manager, Artist and Client journeys accepted. |
| Production readiness | Migrations, seeds, secrets, backups, monitoring, rollback and smoke tests proven. |
| Critical defects | No unresolved P0/P1 launch-blocking defect. |

# 16. Executive Confirmation - Decisions Being Requested

The following confirmation creates one clear management baseline for the development team and prevents later ambiguity about what was or was not included in the approved Phase 1 commitment.

| # | Executive confirmation |
| --- | --- |
| 1 | Phase 1 consists of three products: Admin Panel, Artist App and Client Booking App, operating on one shared backend and database. |
| 2 | The approved Phase 1 FSD Main Success Scenarios define the intended user journeys, subject to newer approved contracts where a later rule supersedes older FSD wording. |
| 3 | UI/UX can be refined during implementation without reopening backend architecture when the change is visual or interaction-only. |
| 4 | Material behaviour/data/API/RBAC/state changes require controlled review and may affect delivery. |
| 5 | Phase 1 excludes the explicitly deferred Phase 2 items listed in this document unless separately approved with impact assessment. |
| 6 | The delivery model uses one Backend Developer, one Admin Frontend Developer, one App Developer and heavy Hermes agent execution under human review gates. |
| 7 | The target is a deployment-ready Phase 1 in 50 days from formal approval/scope freeze, subject to dependencies, approvals and change control. |
| 8 | Any delay in business confirmation or approved material scope change may shift the planned deployment date. |
| 9 | Go-live occurs only after defined booking, payment, RBAC, UAT and production-readiness gates pass; schedule pressure does not override stop-ship controls. |

## Executive Sign-Off

| Name |  |
| --- | --- |
| Designation | CEO / Authorized Business Approver |
| Decision | Approved / Approved with Changes / Not Approved |
| Signature |  |
| Date |  |

If approved with changes, attach the change list or reference the approved Change Request IDs. Only those documented changes modify this baseline.

# Appendix A - Current Phase 1 Development Documentation Set

The following documents collectively support development. The exact file version in the controlled project folder should be used.

| Area | Authoritative / Supporting Document |
| --- | --- |
| Business Requirements | YOYO Business Requirements Document |
| Admin FSD | YOYO Admin Panel FSD Final |
| Artist FSD | YOYO Artist App FSD Final |
| Client FSD | YOYO Booking App FSD Final |
| User Stories | YOYO Phase 1 User Stories - development-ready; to be refreshed to latest decisions |
| ERD | YOYO Phase 1 Revised ERD v2.2 - current structural baseline |
| Booking / Availability | Booking and Availability Contract v1.1 |
| Booking Lifecycle | Booking State Machine v1 |
| Consultation / Consent | Artist Consultation and Digital Consent Contract v1 |
| Service Session | Artist App Service Session State Machine v1 |
| Money Rules | Payment and Money Rules Contract v1 |
| Payment / Refund | Payment and Refund State Machine v1 |
| Membership | Membership State Machine v1 |
| RBAC | RBAC and Permission Matrix v1 |
| API | API and Data Contract v1 |
| Validation | Validation and Error Handling Contract v1 |
| Delivery Plan | 50-Day Deployment Execution Plan - CEO Proposal v1 |
| Remaining readiness docs | RTM, UAT/E2E Test Plan, Seed & Configuration Specification, Deployment/Go-Live Specification, Change & Decision Register, refreshed User Stories |

## Appendix B - One-Sentence CEO Summary

PHASE 1 IN ONE SENTENCE YOYO Phase 1 delivers one shared salon operating backend through an Admin Panel, Artist App and Client Booking App, with documented booking, payment, membership, consultation, session and permission rules, targeted for deployment readiness within 50 days from formal scope approval under controlled change management.

# 2026-08-21 Current Phase 1 Alignment

Status: CURRENT IMPLEMENTATION AUTHORITY

This section records approved Phase 1 rules and enhancements as of 21 August 2026. Any earlier wording elsewhere in this document that conflicts with this section is superseded and must not be implemented.

• Architecture: Admin Panel, Artist App and Client Booking App use one shared backend/API and one PostgreSQL source of truth. Phase 1 is single-branch.

• Artist assignment: Phase 1 has no automatic artist selection. YOYO Assigned Team / Auto Assign enters a manual assignment queue. Authorized Admin/Floor-Manager capability assigns eligible artist(s). Check-in never chooses the artist. AUTO_STANDARD is reserved for Phase 2 only.

• Two-artist services: service master drives required_artist_count = 1 or 2. No hardcoded Senior+Junior rule. For a two-artist service, requested artist is lead and support is assigned separately; start is blocked until fully assigned.

• Consultation: Artist fills consultation; client does not edit/sign the salon consultation. New client = full consultation. Returning client = No Changes review reference or Update with a new prefilled immutable version. High-risk digital service consent is a separate configurable gate.

• Booking timing: 60-day horizon, 15-minute slots, 10-minute artist-only post-service buffer, 30-minute same-day self-booking lead time, and an 8-minute online payment hold.

• Specific artist: 31–60 day specific-artist bookings are PROVISIONAL and revalidated at T-30; no silent artist substitution.

• Advances: Direct Creative Director booking = fixed ₹5,000 mandatory advance. Every other pre-book path = 20% mandatory advance. YOYO Assigned Team remains 20% even if a Creative Director is later manually assigned.

• Creative Director reschedule: the ₹5,000 advance may transfer to the newly rescheduled appointment.

• Group booking: each group member receives an independent booking/appointment linked by a group container. Each member/service advance is calculated independently (20% of each service price, except direct CD rule). Individual member appointments may be cancelled/rescheduled independently. A combined checkout is permitted only when backend allocation remains exact per appointment/service.

• Tips: no tip control exists in the Client App. Normal tip is cash directly from client to artist. If client asks to include a tip on the salon bill, Receptionist/Admin may add the client-requested amount at the billing desk and attribute it to intended artist(s).

• Refunds: YOYO issues no cash refunds. Approved destination is eligible original electronic source or YOYO Wallet, according to client choice; eligible membership refund flows remain only where explicitly allowed.

• Payment reconciliation: uncertain provider payments move from ordinary PENDING to RECONCILIATION_REQUIRED after 15 minutes; daily unresolved-payment reconciliation sweep.

• Membership expiry: unused balance is preserved/frozen. On renewal, Admin may carry forward/transfer preserved balance. Primary holder cannot be changed/removed; sub-members can be changed within slot limits.

• Early membership renewal: if current membership still has balance, successor term begins on exact current expiry date; if current balance is zero, renewed membership may activate immediately on renewal date.

• Support channels: Meta WhatsApp Cloud API primary; MSG91 SMS fallback. First-response operational targets: High 30 minutes, Medium 2 hours, Low 8 business hours.

• Approved CRM additions: Customer 360, Unified Client Timeline, Personalized Smart Suggested Slots, Next Best Action, Rebooking/Lapsed Client Intelligence, Advanced Notifications Center, Product Recommendations v1, and existing Admin Content Controls.

• Explicitly not added: Client Attention Queue, Client Segments, Customer Health Score, Relationship Alerts, Membership Intelligence dashboard, and Service Affinity dashboard.

• Client AI Assistant: tool-using assistant can discover services/artists/products, answer account questions, check availability, book/reschedule/cancel through the same authorized APIs/state machines, surface suggested slots, wallet/membership/booking information and support. It never writes directly to the database or bypasses confirmation/payment/RBAC.

• Artist AI Assistant: tool-using operational copilot can answer permitted questions about the artist's schedule, next appointment, assigned/current client context, consultation/safety data, services/products, session status, personal business/performance figures and notifications. It uses authorized APIs only and cannot bypass scope/RBAC.

## Four intentionally open items

• OPEN-01 — Final GST / tax / HSN-SAC / invoice statutory configuration (pending current invoice evidence).

• OPEN-02 — Final artist revenue-allocation basis/formula (pending accountant confirmation).

• OPEN-03 — Exact service-master rows requiring two artists.

• OPEN-04 — Exact high-risk service list and final legal consent wording.

Developers must keep these four values configuration-driven and must not invent production values. They do not block general development, but they block final UAT/production activation of the directly affected behavior.

# Approved Phase 1 scope expansion - 21 August 2026

• Customer 360 and Unified Client Timeline in Admin Panel.

• Personalized Smart Suggested Slots in Client App with Admin promote/suppress controls.

• Deterministic Next Best Action and Rebooking/Lapsed Intelligence in Customer 360.

• Advanced Notifications Center across Client/Artist/Admin relevant events.

• Product Recommendations v1 using existing data/configuration.

• Client AI Assistant and Artist AI Assistant as authorized tool-using interfaces over existing APIs.

Not added: Client Attention Queue, Client Segments, Customer Health Score, Relationship Alerts, Membership Intelligence dashboard, Service Affinity dashboard.

Delivery baseline is revised to 58 planned calendar days from formal development start, with an internal stretch target driven by dependency-ready node completion. The detailed dependency/node plan is produced separately after UI scope freeze.